## Inputs
Project Inputs & Assumptions
899 Virginia Park St, Detroit MI 48202 — Claim 061004792 (Liberty Mutual) — DOL 02/26/2026 — Freezing / attic supply line
Edit YELLOW cells only. All quantities and totals recalculate automatically.
Parameter | Value | Unit | Notes / Source
Floor 1 area (SF) | 940.7 | SF | Actual — Xactimate sketch '1st floor', claim 061004792
Floor 2 area (SF) | 956.28 | SF | Actual — sketch '2nd floor 2'
Floor 3 / attic finished area (SF) | 541.73 | SF | Actual — sketch '3rd floor 2'
Average ceiling height (FT) | 9 | FT | Historic homes often 9-10 ft on lower floors
Wall+ceiling surface multiplier (x floor area) | 4.56 | x | Actual: 11,112 SF walls+ceilings above grade / 2,439 SF floor (basement B1 2 adds 3,471 SF surface, excluded)
Electrical openings per 100 SF floor | 2.5 | EA | Outlets + switches + fixtures; NEC receptacle spacing will add openings vs. original
Detroit location factor (RS Means CCI) | 1.05 | x | User to validate against current RS Means City Cost Index for Detroit
GC overhead & profit | 18% | % | Typical 15-22% on insurance restoration work
Contingency | 10% | % | Hidden conditions: hazmat, framing rot, code items
Wall finish system toggle (1 = drywall+skim, 2 = 3-coat plaster) | 1 | - | Set to 2 if insurer owes like-kind lath & plaster
Derived Quantities
Total floor area (SF) | 2438.71
Total wall + ceiling surface (SF) | 11120.5176
Electrical openings (EA) | 61
Legend:
Yellow / blue = edit these ¦ Black = formula, do not edit ¦ Green = pulls from another sheet

## Estimate
Restoration Estimate — Line Item Detail
Unit costs are 2026 national-average ranges (installed, incl. labor+material) before location factor. Validate every line against RS Means and enter the Means unit cost in col K/L.
CSI Div | Item Description | Unit | Qty | Unit $ Low | Unit $ High | Ext. $ Low | Ext. $ High | RS Means Line # | Means Unit $ | Means Ext. $ | Variance vs Mid | Notes
MECHANICAL
23 52 | Boiler combustion/safety inspection & service (ran dry — check sections, LWCO) | LS | 1 | 350 | 700 | 350 | 700 |  |  |  |  | If sections cracked from dry-firing, see replacement line
23 52 | Boiler replacement contingency (cast-iron, hydronic, ~150-200 MBH) | LS | 1 | 8000 | 16000 | 8000 | 16000 |  |  |  |  | Carry as contingency until inspection report; delete line if boiler passes
23 82 | Radiator system drain, refill, bleed, TRV/valve repacking allowance | LS | 1 | 800 | 2000 | 800 | 2000 |  |  |  |  | 3 floors of radiators disturbed by demo
22 11 | Repair/replace burst domestic supply line at attic + isolation valves | LS | 1 | 1500 | 3500 | 1500 | 3500 |  |  |  |  | Cause of loss — insurer covers resulting damage; pipe itself may be excluded
22 07 | Re-insulate attic domestic piping (freeze protection) | LS | 1 | 500 | 1500 | 500 | 1500 |  |  |  |  | Root-cause prevention; may be code/ordinance item
| MECHANICAL SUBTOTAL |  |  |  |  | 11150 | 23700 |  |  | 0
ELECTRICAL
26 05 | Full knob & tube rewire — copper NM, all branch circuits (walls open) | SF | 2438.71 | 8 | 14 | 19509.68 | 34141.94 |  |  |  |  | Open-wall condition = low end of $10-20/SF market range
26 24 | Service/panel upgrade to 200A + grounding electrode system | LS | 1 | 2500 | 4500 | 2500 | 4500 |  |  |  |  | K&T homes typically 60A service; likely required by code
26 27 | Period-style wiring devices (push-button switches, plates) premium | EA | 61 | 25 | 60 | 1525 | 3660 |  |  |  |  | Premium over builder-grade; historic character line item
26 05 | AFCI/GFCI protection + smoke/CO interconnect (code-required) | LS | 1 | 1200 | 2500 | 1200 | 2500 |  |  |  |  | Ordinance & Law coverage candidate
26 05 | Electrical permits & inspections (City of Detroit) | LS | 1 | 300 | 900 | 300 | 900
| ELECTRICAL SUBTOTAL |  |  |  |  | 25034.68 | 45701.94 |  |  | 0
STRUCTURAL
06 11 | Attic framing/sheathing repair at burst location — allowance | LS | 1 | 2000 | 6000 | 2000 | 6000 |  |  |  |  | Scope TBD after demo exposes framing
06 11 | Joist/subfloor sistering & repair allowance (saturated members) | LS | 1 | 1500 | 5000 | 1500 | 5000 |  |  |  |  | Water traveled 3 floors; probe after demo
02 87 | Antimicrobial treatment / mold remediation of framing cavities | SF | 2438.71 | 1 | 3 | 2438.71 | 7316.13 |  |  |  |  | Priced on affected floor area; adjust to actual affected SF
02 26 | Asbestos survey (plaster, pipe insulation) + lead paint XRF | LS | 1 | 500 | 1200 | 500 | 1200 |  |  |  |  | Pre-1978 home — required before demo in most jurisdictions
| STRUCTURAL SUBTOTAL |  |  |  |  | 6438.71 | 19516.13 |  |  | 0
ARCHITECTURAL
02 41 | Demolition — plaster & lath walls/ceilings, bag & dispose | SF | 11120.5176 | 2 | 4 | 22241.0352 | 44482.0704 |  |  |  |  | Includes dumpsters; lead-safe practices below
02 83 | Lead-safe containment premium (RRP): poly, neg. air, HEPA clean | SF | 11120.5176 | 0.5 | 1.5 | 5560.2588 | 16680.7764 |  |  |  |  | EPA RRP compliance, pre-1978
07 21 | Insulation — exterior wall cavities + attic (code upgrade) | SF | 2438.71 | 1.5 | 3.5 | 3658.065 | 8535.485 |  |  |  |  | Ordinance & Law candidate; walls open = cheap to do now
09 29 | Drywall 1/2" hang, tape, finish L4 — walls & ceilings | SF | 11120.5176 | 2.5 | 4 | 27801.294 | 44482.0704 |  |  |  |  | Active when Inputs toggle = 1
09 23 | Veneer skim coat over drywall (plaster-look finish) | SF | 11120.5176 | 1.5 | 3 | 16680.7764 | 33361.5528 |  |  |  |  | Active when Inputs toggle = 1
09 23 | ALTERNATE: 3-coat plaster on lath, like-kind historic | SF | 0 | 12 | 25 | 0 | 0 |  |  |  |  | Active when Inputs toggle = 2 — like-kind & quality claim basis
09 91 | Prime + 2 coats paint — all new wall/ceiling surfaces | SF | 11120.5176 | 1.5 | 3 | 16680.7764 | 33361.5528
06 22 | Remove, salvage, reinstall/replicate trim, casing, base — allowance | LS | 1 | 4000 | 9000 | 4000 | 9000 |  |  |  |  | Historic profiles; replication where damaged
08 14 | Interior doors — rehang, adjust, hardware allowance | LS | 1 | 1000 | 3000 | 1000 | 3000
09 64 | Sand & refinish existing hardwood floors (2 coats poly) | SF | 2438.71 | 4 | 8 | 9754.84 | 19509.68 |  |  |  |  | Floors mostly intact per owner; board replacement below
09 64 | Hardwood board replacement allowance (cupped/stained boards) | LS | 1 | 1500 | 5000 | 1500 | 5000 |  |  |  |  | Adjust after floors dry & are inspected
01 74 | Final construction clean, 3 floors | SF | 2438.71 | 0.5 | 1 | 1219.355 | 2438.71
| ARCHITECTURAL SUBTOTAL |  |  |  |  | 110096.4008 | 219851.8978 |  |  | 0
FURNISHINGS
12 00 | Contents pack-out, inventory, storage (3 months), pack-back | LS | 1 | 3500 | 9000 | 3500 | 9000 |  |  |  |  | Often paid under Contents/ALE coverage, not Dwelling
12 00 | Contents cleaning/restoration allowance (soft goods, upholstery) | LS | 1 | 1500 | 5000 | 1500 | 5000 |  |  |  |  | Placeholder pending contents inventory
12 20 | Window treatments — clean/replace allowance | LS | 1 | 500 | 2000 | 500 | 2000
12 00 | Damaged furnishings replacement — placeholder for itemized inventory | LS | 1 | 0 | 0 | 0 | 0 |  |  |  |  | Owner to attach itemized contents list with RCV/ACV
| FURNISHINGS SUBTOTAL |  |  |  |  | 5500 | 16000 |  |  | 0

## Summary
Estimate Summary
Historic 3-Story Residence — Attic Supply Line Failure — Detroit, MI — Ballpark for insurance discussion only; not a bid
Division | Low | High | RS Means (as entered)
Mechanical | 11150 | 23700 | 0
Electrical | 25034.68 | 45701.94 | 0
Structural | 6438.71 | 19516.13 | 0
Architectural | 110096.4008 | 219851.8978 | 0
Furnishings | 5500 | 16000 | 0
Direct cost subtotal | 158219.7908 | 324769.9678 | 0
Detroit location factor adj. | 7910.9895 | 16238.4984 | 0
GC overhead & profit | 29903.5405 | 61381.5239 | 0
Contingency | 16613.078 | 34100.8466 | 0
TOTAL ESTIMATE | 212647.3988 | 436490.8367 | 0
Total floor area (SF) | 2438.71
Cost per SF of floor area | 87.1967 | 178.9843
Insurance notes for adjuster discussion:
1. Like-kind & quality: original finish is lath & plaster. Set Inputs toggle = 2 to price the plaster alternate the policy may owe.
2. Ordinance & Law: K&T rewire, AFCI/GFCI, insulation, and panel upgrade are code-mandated once walls open — check O&L sublimit.
3. Boiler: dry-fired cast iron can crack. Get the inspection report in writing before releasing the contingency line.
4. Contents/ALE: pack-out and furnishings usually paid under separate coverages — do not let them dilute the Dwelling limit.
5. Sources: 2026 national cost guides (HomeGuide, Angi/Homewyse, contractor pricing); validate each line against RS Means using cols J-M on the Estimate tab.

## Adjuster Comparison
Liberty Mutual Estimate vs. Model — Claim 061004792
Adjuster direct costs from 'Recap by Category' (contractor estimate pp.30-31), mapped to divisions. Compare vs Estimate tab (which excludes location factor/O&P/contingency at line level).
Division | Liberty Direct $ | Model Low | Model High | Assessment
Mechanical | 33721.59 | 11150 | 23700 | COVERED WELL. HVACi boiler+radiators $30,875 RCV carried in full (line 2, w/ 20% O&P = $37,050). Plumbing rem/resets included.
Electrical | 837.19 | 25034.68 | 45701.94 | MAJOR GAP. Line 3 'Bid Item, Electrical' = $0.00 open item pending city inspection. K&T rewire realistically $20-35K. Largest supplement opportunity.
Structural | 274.37 | 6438.71 | 19516.13 | GAP. Only underlayment carried. No framing repair at burst location, no joist probe, NO antimicrobial/mold treatment despite loss 2/26 and inspection 6/22 (4 months wet).
Architectural | 111308.49 | 110096.4008 | 219851.8978 | PARTIAL SCOPE. Full oak floor tear-out/replace ($46.7K — generous) but plaster is SPOT repair only (e.g. Living Rm: 66 of 625 SF walls). No lead-safe RRP containment, no insulation.
Furnishings | 1884.74 | 5500 | 16000 | GAP. Only content manipulation + blinds. No pack-out/storage, no contents cleaning. Pursue under Contents coverage separately — don't dilute Dwelling.
Direct cost subtotal | 148026.38 | 158219.7908 | 324769.9678
Liberty Claim Payment Waterfall (as issued 07/10/2026)
Replacement Cost Value (RCV) | 179578.08 | Subtotal $177,632.08 + $1,946 MI sales tax on materials
Less recoverable depreciation | -26641.23 | 50% dep on materials only — RECOVERABLE on completion of repairs
Net ACV on Coverage Building | 152936.85
Less deductible | -5000
Net estimate (check today) | 147936.85
Net if depreciation recovered | 174578.08 | Submit completion invoices to recover the $26,641
Coverage A limit | 776800 | Ample headroom for supplements — limit is NOT the constraint
Supplement Strategy — priority order
1. ELECTRICAL ($0 open item): Get the City of Detroit electrical inspection scheduled NOW. Walls will be open — the K&T rewire supplement ($20-35K) hinges on that inspection report. Line 3 of the estimate explicitly leaves the door open.
2. MOLD/ANTIMICROBIAL: 4 months elapsed between loss and inspection. Have an industrial hygienist or IICRC remediation firm document cavity conditions during demo. Supplement immediately if found — resulting mold from a covered water loss is typically covered (check sublimit).
3. PLASTER SCOPE: Liberty scoped spot plaster repair (~2,000 of 11,112 SF surface). If demo reveals plaster keys sheared/delaminated beyond scoped areas, document per-room with photos and supplement. Their own line items ($6.82-7.80/SF, 3-coat) become the agreed unit price — good pricing to extend.
4. LEAD-SAFE RRP: Pre-1978 home; EPA RRP containment is legally required for the contractor and is a compensable cost not in the estimate (~$0.50-1.50/SF disturbed).
5. PERMITS ($0 open item, line 4): Submit actual permit receipts as incurred.
6. DEPRECIATION RECOVERY: $26,641 is recoverable — keep every invoice, submit at completion.
7. CONTENTS/ALE: Pack-out, storage, contents cleaning are absent. File under Coverage C (Contents) and ALE if the house is uninhabitable — separate limits from the $776,800 Dwelling.